## DEVIATION
DEVIATION LIST
Ship Type. | 48,000 cbm LPG Carrier | Hull No. | YZJ2023-1584/1585 | Seller | TECHCROSS | Page | 1 Page
선종 |  | 호선 |  | 공급자 |  | 페이지
Machinery | BWMS(ECS) | CLASS | NK | FLAG | SINGAPORE | Date | 25.08.11.
장비명 |  | 선급 |  | 국기 |  | 날짜
Serial No. | POR Specification Requirement | Seller Proposal |  | Buyer's Decision |  | Remarks
일련번호 | 구매요구서 요구사항 | 공급자 제안사항 |  | 구매자 결정사항 |  | 비고
Technical POS Part II | 3 The installation tools even not mentioned in the TA which is necessary for equipment installation should be supplied by maker for free. | 당사는 장비만 공급하며, 설치 및 기타 자재는 YARD SCOPE입니다. 영업팀 확인 부탁드립니다.
Technical POS Part II | 4 The equipment factory shall bear the delivery fee for the approval drawings, working drawings and final drawings etc. | 영업팀 확인 부탁드립니다.
Technical POS Part II | 6 ______ main ballast pump and ______ stripping pumps should be parallel operated at the same time during de-ballasting. | Detailed specification of neutralization equipment will be rechecked at the approval stage.
Technical POS Part II | 7 RS485 modbus should be come/to RCV system | BWTS is not necessary to be monitored and interfaced to RCV. Because Control PC which is provided by maker will be installed in CCR(near RCV). And, it can monitor and control BWTS.
Technical POS Part II | 15 The manufacturer shall provide mooring test procedures and trial trial procedures | Mooring test is not applicable for BWMS. BWMS FAT procedure and BWMS commissioning procedure can be submitted.
Technical POS Part II | 16 The filter must meet the maximum discharge of the ballast pump | Our treatment system is direct Electrolysis type BWTS without Filter.
Technical Agreement 12/30 | 20.Others 1) The connecting diameter of flange is according to ISO standard. All the flange drawing should be provided by maker. | The flange type for our equipment is JIS type. Please confirm. 영업팀 담당자님 카운터 플랜지 공급 여부 확인 부탁드립니다.
Technical Agreement 12/30 | 20.Others 9) The mooring test procedure of all equipments to be supplied by maker in the approval drawing. | Mooring test is not applicable for BWMS.